## Audit_Summary
Control ID | Status | Risk Level | Summary | Owner
IA-2 | Deficient | Medium | No MFA configuration evidence provided | IAM Team
AU-2 | Pass | Low | Splunk log ingestion validated | Security Ops
SC-8 | Deficient | High | Application observed running over HTTP | Infra Team
AC-2 | Pass | Low | Basic access control evidence reviewed | App Owner
AU-6 | Pending | Medium | No documented log review process provided | Security Ops

## Control_Matrix
Control ID | Control Name | Objective | Evidence Required
AC-2 | Account Management | Validate account creation and role handling | User/account screenshots, admin controls
IA-2 | Identification and Authentication | Validate authentication strength | Login screenshots, MFA evidence if available
AU-2 | Audit Events | Validate security-relevant events are logged | Splunk searches, event screenshots
AU-6 | Audit Review | Validate logs can be reviewed/analyzed | Splunk dashboard/search evidence
SC-8 | Transmission Confidentiality | Validate data protection in transit | HTTPS/TLS evidence or finding
SC-28 | Protection of Information at Rest | Validate stored data is protected | App or config review
PL-8 | Security and Privacy Architecture | Validate documented data flow/architecture | Architecture diagram
CA-7 | Continuous Monitoring | Validate recurring review/monitoring process | Tracker, retest notes

## Evidence Inventory
Evidence ID | Control | File Name | Location | Source | Date Collected
E-001 | AU-2 | splunk-ingestion-success.png | 04-Evidence/Logging | Splunk | 2026-04-24
E-002 | AU-2 | splunk-search-results.png | 04-Evidence/Logging | Splunk | 2026-04-24
E-003 | AC-2 | login-page.png | 04-Evidence/Access-Control | Web App | 2026-04-24
E-004 | SC-8 | http-browser.png | 04-Evidence/Encryption | Browser | 2026-04-24
E-005 | IA-2 | user-account.png | 04-Evidence/Access-Control | Web App | 2026-04-24

## Findings Register
Finding ID | Control | Description | Risk | Impact | Recommendation | Status
F-001 | SC-8 | Application running over HTTP | High | PII exposure in transit | Enable HTTPS/TLS | Open
F-002 | IA-2 | MFA not implemented | Medium | Account compromise risk | Implement MFA | Open
F-003 | AU-6 | No log review process | Medium | Threats may go undetected | Define monitoring procedures | Open

## Remediation Tracker
Finding ID | Action Required | Owner | Due Date | Status | Retest Result
F-001 | Implement HTTPS/TLS | Infra Team | 2026-05-15 | Open | Pending
F-002 | Enable MFA | IAM Team | 2026-05-15 | Open | Pending
F-003 | Define log review process | Security Ops | 2026-05-20 | Open | Pending

## Evidence Requests
Request ID | Control | System | Evidence Requested | Owner | Status | Risk Level | Date Requested | Date Received | Validation Status | Objective | Notes
ER-001 (MFA) | IA-2 | Web App | MFA configuration proof | IAM Team | Pending | Medium | 2026-04-24 | (leave blank) | Pending | Ensure strong authentication mechanisms | No MFA configuration evidence provided. Control validation pending response from IAM team.
ER-002 (Logs) | AU-2 | Splunk | Log ingestion evidence | Security Ops | Closed | Low | 2026-04-24 | 2026-04-24 | Valid | Ensure security-relevant events are logged | Log ingestion verified in Splunk. Events are searchable and attributed to host pii-lab-webapp. Evidence satisfies AU-2 requirements.
ER-003 (TLS) | SC-8 | Web App | TLS/HTTPS config proof | Infra Team | Closed | High | 2026-04-24 | 2026-04-24 | Deficient | Protect data in transit | Application observed operating over HTTP. No TLS certificate identified. Evidence does not meet SC-8 transmission confidentiality requirements.
ER-004 (Access) | AC-2 | Web App | User role/permission structure | App Owner | Received | Low | 2026-04-24 | 2026-04-24 | Valid | Enforce proper account and access management | User account functionality reviewed. Basic role separation observed. No excessive privilege identified in current scope.
ER-005 (Log Review) | AU-6 | Splunk | Log review/reporting process | Security Ops | Open | Medium | 2026-04-24 | 2026-04-24 | Pending | Ensure logs are reviewed and analyzed | No documented log review or monitoring process provided. Evidence insufficient to validate AU-6 control.

## PII_Data_Mapping
Data ID | Data Type | Example | System | Storage Location | Encryption (Transit/Rest) | Access Control | Logging | Regulation | Risk Level | Role | Notes
PII-001 | Email Address | user@email.com | Web App | Application Database | None (HTTP) | Basic login only | Partial (Splunk) | CCPA | High | Application Owner | No TLS encryption; data exposed in transit
PII-002 | Full Name | John Doe | Web App | Application Database | None | User-based access | Partial | CCPA | Medium | Application Owner | Stored without clear protection controls
PII-003 | Password | ******** | Web App | Application Backend | Unknown | Application-controlled | Not visible | CCPA | High | IAM Team | MFA not implemented; authentication controls not validated
PII-004 | User Activity | Logins / Access Events | Splunk | SIEM (Splunk Index) | Internal | Security Ops access | Yes | CCPA | Low | Security Operations | Logging present but no defined review process
PII-005 | Phone Number | 555-123-4567 | Web App | Application Database | None | Basic login only | Partial | CCPA | High | Application Owner | No encryption and no validation of access restrictions

## Audit Notes
04/24 – Logging validated via Splunk ingestion (AU-2)
04/24 – Application observed running over HTTP (SC-8 failure)
04/24 – No MFA evidence provided (IA-2 gap)
04/24 – No log review process identified (AU-6 gap)